## Group member 1
To-do list
To be completed by: |  |  |  | Name: Carlo Ace Sagad
Deadline: |  |  | 2024-02-19 | Date: 02-15-2024
PHW 2
% done | Task | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-02-15 | 2024-02-19 |  | 1
100% | Preparation | 2024-02-15 | 2024-02-19 |  | 1
100% | Joins Exercise | 2024-02-15 | 2024-02-19 |  | 2
100% | Joins | 2024-02-15 | 2024-02-19 |  | 2
100% | Top 5 | 2024-02-15 | 2024-02-19 |  | 2
100% | Notebook | 2024-02-18 | 2024-02-19 |  | 2
100% | Recording | 2024-02-19 | 2024-02-19 |  | 1
100% | Final Review | 2024-02-19 | 2024-02-19 |  | 1
100% | Submission | 2024-02-19 | 2024-02-19 |  | 1

## Group member 2
To-do list
To be completed by: |  |  | 2024-02-19 | Name: Bin Xie
Deadline: |  |  | 2024-02-19 | Date: 2/15/24
Project 1
% done | Task | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-02-15 | 2024-02-19 | 2024-02-19 | 1
100% | Preparation | 2024-02-14 | 2024-02-19 | 2024-02-19 | 1
100% | Exercise | 2024-02-15 | 2024-02-19 | 2024-02-19 | 2 | split it to 5 parts to team
100% | Queries | 2024-02-16 | 2024-02-19 | 2024-02-19 | 2 | split it to 5 parts to team
100% | Top 5 queries | 2024-02-17 | 2024-02-19 | 2024-02-19 | 2
100% | Notebook | 2024-02-18 | 2024-02-19 | 2024-02-19 | 3 | discuss in team to fighure it out
100% | Recording | 2024-02-19 | 2024-02-19 | 2024-02-19 | 1 | split to 3 videos
100% | Final review | 2024-02-19 | 2024-02-19 | 2024-02-19 | 1 | review as a team
100% | Submission | 2024-02-19 | 2024-02-19 | 2024-02-19 | 1

## Group member 3
To-do list
To be completed by: |  |  | 2024-02-19 | Name: Taruna Mangar
Deadline: |  |  | 2024-02-19 | Date: 02/19/2024
Project 1
% done | Task | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-02-15 | 2024-02-15 |  | 1
100% | Preparation | 2024-02-15 | 2024-02-16 |  | 2
100% | Join Excercies | 2024-02-16 | 2024-02-16 |  | 1
100% | Joins | 2024-02-17 | 2024-02-17 |  | 1
100% | NoteBook Review | 2024-02-17 | 2024-02-17 | 2024-02-18 | 2 | Ensure all objects are in PascalCase and indicate what's special.
100% | Recording | 2024-02-17 | 2024-02-17 | 2024-02-18 | 2 | Capture all queries
100% | Final Review | 2024-02-18 | 2024-02-18 | 374059 | 2 | Ensure all needed corrections were made.
100% | Submission | 2024-02-19 | 2024-02-19 |  | 1

## Group member 4
To-do list
To be completed by: |  |  | 2024-02-19 | Name Ileana Aguilar
Deadline: |  |  | 2024-02-19 | Date 2/15/24
PHW 2
% done | Task | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-02-15 | 2024-02-15 |  | 0
100% | Preparation | 2024-02-15 | 2024-02-16 |  | 1
100% | Joins Exercise | 2024-02-15 | 2024-02-16 | 2024-02-18 | 1 | I had trouble with my database connection
100% | Joins | 2024-02-15 | 2024-02-16 | 2024-02-18 | 1 | I had trouble with my database connection
100% | Top 5 | 2024-02-15 | 2024-02-17 | 2024-02-18 | 3 | I had trouble with my database connection
100% | Notebook Review | 2024-02-15 | 2024-02-17 | 2024-02-18 | 3 | Make sure all corrections were made
100% | Recording | 2024-02-18 | 2024-02-18 | 2024-02-19 | 1 | The recording was pushed due to notebook
100% | Final Review | 2024-02-18 | 2024-02-18 | 2024-02-19 | 1 | Make sure all corrections were made
100% | Submission | 2024-02-19 | 2024-02-19 |  | 1

## Group member 5
To-do list
To be completed by: |  |  |  | Name: Arrafi Talukder
Deadline: |  |  |  | Date: 2/19/24
Project 1
% done | Task | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-02-15 | 2024-02-15 |  | 0
100% | Preparation | 2024-02-15 | 2024-02-16 |  | 1
100% | Exercises | 2024-02-16 | 2024-02-17 |  | 1 | See the differences in the outputs between TSQL4 and Northwind databases
100% | Joins Queries | 2024-02-18 | 2024-02-18 |  | 0 | See the differences in the outputs between TSQL4 and Northwind databases
100% | Top 5 Queries | 2024-02-18 | 2024-02-18 |  | 0 | See the differences in the outputs between TSQL4 and Northwind databases
100% | Notebook Review | 2024-02-19 | 2024-02-19 |  | 0 | See if every query is present inside
100% | Recordings | 2024-02-19 | 2024-02-19 |  | 0 | Capture all the queries in the notebook
100% | Final Review | 2024-02-19 | 2024-02-19 |  | 0 | To make sure that all corrections are made and misconceptions are cleared out
100% | Submission | 2024-02-19 | 2024-02-19 |  | 0

## Group member 6
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Task | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up