## Group member 1
To-do list
To be completed by: |  |  |  | Name: Carlo Ace Sagad
Deadline: |  |  | 2024-03-24 | Date: 21-Mar-24
Project1
% done | Task | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-03-18 | 2024-03-21 |  | 1
100% | Preparation | 2024-03-18 | 2024-03-21 |  | 1 | Understanding the Project Requirements
100% | Create JBDC connection) | 2024-03-18 | 2024-03-21 |  | 2 | Manage to connect to SQL Server using JDBC
100% | Create Queries | 2024-03-19 | 2024-03-21 |  | 2 | Creating 20 Queries
100% | Top 3 | 2024-03-20 | 2024-03-21 | 2024-03-24
100% | Worst 3 | 2024-03-20 | 2024-03-21 | 2024-03-24 | 2
100% | Notebook | 2024-03-23 | 2024-03-21 | 2024-03-24
100% | JDBC Java Program | 2024-03-23 | 2024-03-21 | 2024-03-24 | 2
100% | Recording | 2024-03-24 | 2024-03-21 | 2024-03-24 | 1 | Started the Recordings
100% | Final Review | 2024-03-24 | 2024-03-21 | 2024-03-24 | 1
100% | Submission | 2024-03-24 | 2024-03-21 | 2024-03-24 | 1

## Group member 2
To-do list
To be completed by: |  |  | 2024-03-24 | Name: Bin Xie
Deadline: |  |  | 2024-03-24 | Date: 3/24/24
Project1
% done | Task | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-03-13 | 2024-03-24 | 2024-03-24 | 1
100% | Preparation | 2024-03-14 | 2024-03-24 | 2024-03-24 | 1
100% | Create JDBC | 2024-03-15 | 2024-03-24 | 2024-03-24 | 2 | 2 days to complete
100% | Create Queries | 2024-03-18 | 2024-03-24 | 2024-03-24 | 1
100% | Notebook | 2024-03-19 | 2024-03-24 | 2024-03-24 | 2
100% | Top 3 | 2024-03-21 | 2024-03-24 | 2024-03-24 | 1
100% | Worst 3 | 2024-03-21 | 2024-03-24 | 2024-03-24 | 1
100% | JDBC Program | 2024-03-22 | 2024-03-24 | 2024-03-24 | 2 | challeging to figure it out
100% | Recording | 2024-03-24 | 2024-03-24 | 2024-03-24 | 1
100% | Final Review | 2024-03-24 | 2024-03-24 | 2024-03-24 | 1
100% | Submission | 2024-03-24 | 2024-03-24 | 2024-03-24 | 1

## Group member 3
To-do list
To be completed by: |  |  | 2024-03-24 | Name: Taruna Mangar
Deadline: |  |  | 2024-03-24 | 2024-03-24
Project1
% done | Task | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-03-18 | 2024-03-21 |  | 1
100% | Preparation | 2024-03-18 | 2024-03-24 |  | 1
100% | Create JBDC connection | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2 | Delayed due to reading delay
100% | Create Queries | 2024-03-20 | 2024-03-20 |  | 1
100% | Implement Json objects | 2024-03-23 | 2024-03-23 |  | 1
100% | Modify Notebook | 2024-03-23 | 2024-03-23 |  | 1
100% | Recording | 2024-03-24 | 2024-03-24 |  | 1
100% | Final Review | 2024-03-24 | 2024-03-24 |  | 1 | Ensure all needed corrections were made.
100% | Submission | 2024-03-24 | 2024-03-24 |  | 1

## Group member 4
To-do list
To be completed by: |  |  | 2024-03-24 | Name Ileana Aguilar
Deadline: |  |  | 2024-03-24 | Date 3/24/24
Project1
% done | Task | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-03-18 | 2024-03-21 |  | 3
100% | Preparation | 2024-03-18 | 2024-03-24 |  | 3
100% | Create JBDC connection | 2024-03-12 | 2024-03-20 |  | 8
100% | Create Queries | 2024-03-20 | 2024-03-23 |  | 3
100% | Top 3 Queries | 2024-03-23 | 2024-03-23 |  | 1
100% | Top 3 Worst Queries | 2024-03-23 | 2024-03-23 |  | 1
100% | add queries to JDBC File | 2024-03-23 | 2024-03-23 |  | 1
50% | ER Diagrams | 2024-03-23 | 2024-03-23
100% | Modify Notebook | 2024-03-23 | 2024-03-23 |  | 1
100% | Recording | 2024-03-24 | 2024-03-24 |  | 1
100% | Final Review | 2024-03-24 | 2024-03-24 |  | 1 | Ensure all needed corrections were made.
100% | Submission | 2024-03-24 | 2024-03-24 |  | 1

## Group member 5
To-do list
To be completed by: |  |  |  | Name: Arrafi Talukder
Deadline: |  |  |  | Date: 3/24/24
Project1
% done | Task | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-03-20 | 2024-03-20 |  | 1
100% | Preparation | 2024-03-22 | 2024-03-22 |  | 1
100% | Medium Queries | 2024-03-23 | 2024-03-23 | 2024-03-24 | 1 | Understanding how to Join different tables in a query(at least 2 joins)
100% | Complex Queries | 2024-03-23 | 2024-03-23 | 2024-03-24 | 1 | Understanding how to implement scalar functions with multiple joins in the query.
100% | Top 3 Queries | 2024-03-24 | 2024-03-24 | 2024-03-24 | 1
100% | Top 3 Worst Queries | 2024-03-24 | 2024-03-24 | 2024-03-24 | 1
100% | JDBC File | 2024-03-24 | 2024-03-24 | 2024-03-24 | 1
0% | ER Diagrams
100% | Recordings | 2024-03-24 | 2024-03-24 | 2024-03-24 | 1 | Capture all the queries in the notebook and JDBC file
100% | Final Review | 2024-03-24 | 2024-03-24 | 2024-03-24 | 1 | o make sure that all corrections are made and misconceptions are cleared out
100% | Submission | 2024-03-24 | 2024-03-24 | 2024-03-24 | 1

## Group member 6
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Task | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up